## Hoja1
# | Risk | Probability (P) | Impact (I) | Risk (R = P × I) | Level of Risk
1 | Facial recognition failure (false rejection of valid users) | 3 | 5 | 15 | High
2 | Inability to recognize users due to poor lighting or unusual angles | 3 | 4 | 12 | Medium
3 | Low accuracy in certain demographic groups (model bias) | 3 | 4 | 12 | Medium
4 | Presentation attacks (using photos, videos, or masks to trick the system) | 4 | 5 | 20 | High
5 | Integration failures with other systems (databases, APIs, servers) | 3 | 4 | 12 | Medium
6 | Biometric data theft due to unauthorized database access | 2 | 5 | 10 | Medium
7 | Leakage of API credentials or private keys | 3 | 4 | 12 | Medium
8 | Software vulnerabilities exploited by attackers | 3 | 5 | 15 | High
9 | Brute-force or phishing attacks to gain unauthorized access | 3 | 5 | 15 | High
10 | Use of malicious software to alter images and bypass recognition | 3 | 4 | 12 | Medium
11 | Non-compliance with data protection regulations (GDPR, ISO 27001, etc.) | 2 | 5 | 10 | Medium
12 | Improper biometric data storage (risk of exposure) | 3 | 5 | 15 | High
13 | Misuse of biometric data by employees or third parties | 2 | 5 | 10 | Medium
14 | Lawsuits due to system failures (discrimination, authentication errors) | 2 | 4 | 8 | Medium
15 | Legal restrictions on facial recognition in certain countries | 2 | 5 | 10 | Medium
16 | High hardware costs for real-time recognition | 3 | 3 | 9 | Medium
17 | Server connection failures affecting authentication | 4 | 3 | 12 | Medium
18 | Users lose access due to drastic appearance changes (beard, glasses, surgery) | 2 | 3 | 6 | Low
19 | Long authentication delays affecting user experience | 3 | 3 | 9 | Medium
20 | Development delays due to lack of budget or technical resources | 3 | 4 | 12 | Medium
21 | Fight with another teammate | 3 | 3 | 9 | Medium
22 | Psychological discomfort (users feel monitored or unsafe using facial recognition) | 3 | 3 | 9 | Medium
23 | Identity theft (face images stolen and used for fraud) | 2 | 5 | 10 | Medium
24 | Harassment or discrimination based on facial recognition data | 2 | 4 | 8 | Medium
25 | Users unable to access their accounts due to physical changes (injuries, aging, makeup) | 3 | 3 | 9 | Medium
26 | Users feel forced to use facial recognition despite privacy concerns | 2 | 4 | 8 | Medium